## Slide 1
Current Architecture
All components in us-east-1 only — single region, no DR capability
1 / 7
Data Mesh Multi-Region Resiliency — April 2026
Producers
Data Mesh Platform
Compute Platforms
Governance (Immuta)
Consumer Notifications
Consumers
us-east-1 (N. Virginia) — ALL COMPONENTS
PRODUCTION
PRODUCERS (each in own AWS account)
Producer A
S3 (Parquet) us-east-1
Producer B
S3 (Iceberg) us-east-1
Producer C
S3 (Parquet) us-east-1
Producer N...
S3 us-east-1
▼ Register Dataset / Notify "New Data Available" ▼
Data Mesh Platform (Platform AWS Account, us-east-1)
Registration APIs: Route53 → ALB → ECS Services
Producer Notification API: Lambda — receives from producers, writes DynamoDB, updates Glue
Consumer Notification API: Lambda — publishes SNS → SQS, pushes to On-Prem Kafka via DX/VPN
Infrastructure: DynamoDB (Metadata) • SNS Topic • Glue Catalog • S3 VPC Endpoint • Notification Polling API (ECS+DDB)
▼ S3 VPC Gateway Endpoint → Producer S3 Buckets ▼
COMPUTE PLATFORMS
Snowflake (us-east-1)
External Tables (Parquet) Unmanaged Iceberg Tables Storage Integrations → east1 S3
Starburst (us-east-1)
Glue Catalog as Metastore S3 Access Point Aliases VPC Gateway Endpoint
Databricks (us-east-1)
External Tables Unity Catalog Metastore IAM Roles → east1 S3
Immuta Governance (Governance Team Account, us-east-1)
Starburst: Runtime API calls (hard dependency) • Snowflake: Native policy sync • Databricks: Native policy sync
Consumer Notification Layer (us-east-1)
Ch 1: SNS → SQS — Platform SNS to Consumer SQS (consumer accounts, east1)
Ch 2: On-Prem Kafka — Lambda/ECS pushes to Kafka via Direct Connect/VPN
Ch 3: Polling API — REST API (ECS + DynamoDB) — Consumer polls for notifications
Consumers (us-east-1)
Query via Snowflake / Starburst / Databricks • Notified via SNS-SQS / Kafka / Polling API
⚠ Single Point of Failure: A full us-east-1 outage renders the entire platform unavailable — APIs, compute, governance, notifications, all consumer queries.

## Slide 2
Ideal State — Proposed Architecture
Both regions fully provisioned: us-east-1 (Production) + us-west-2 (DR Warm Standby)
2 / 7
Data Mesh Multi-Region Resiliency — April 2026
● ACTIVE = Production ● STANDBY = DR Ready ══▶ Cross-region sync (always active) All producers, platform, consumers have infra in BOTH regions
us-east-1 (N. Virginia)
PRIMARY / PRODUCTION
us-west-2 (Oregon)
SECONDARY / DR
PRODUCERS — Active Write
Prod A
S3 east1 PRIMARY WRITE
Prod B
S3 east1 PRIMARY WRITE
Prod C
S3 east1 PRIMARY WRITE
▼
Platform [ACTIVE]
Registration API (ECS/ALB) [ACTIVE]
Producer Notif API (Lambda) [ACTIVE]
Consumer Notif API (Lambda) [ACTIVE] — Publishes to BOTH SNS topics
DynamoDB [PRIMARY WRT] • SNS • Glue • Polling API
COMPUTE PLATFORMS [ACTIVE]
Snowflake
ExtTbl, Iceberg Storage Integ.
Starburst
Glue, S3 AccPt VPC Endpoint
Databricks
ExtTbl, Unity Catalog
S3 VPC Gateway Endpoint → Producer S3 Buckets (east1)
Immuta [ACTIVE] — SB runtime • SF sync • DBX sync
Consumer Notifications [ACTIVE]
SNS→SQS: Consumers poll east1 SQS
Kafka: via east1 DX/VPN
Polling API: ECS + DynamoDB
Consumers [ACTIVE] — SQS east1 • Query SF/SB/DBX east1 • Use CNAME
PRODUCER S3 REPLICAS
Prod A
S3 west2 REPLICA (CRR)
Prod B
S3 west2 REPLICA (CRR)
Prod C
S3 west2 REPLICA (CRR)
▼
Platform [WARM STANDBY]
Registration API (ECS/ALB) [STBY] — min task count
Producer Notif API (Lambda) [DEPLOYED]
Consumer Notif API (Lambda) [DEPLOYED] — SNS west2 receives dual-pub
DynamoDB [REPLICA RO] • SNS • Glue • Polling API
COMPUTE PLATFORMS [WARM STANDBY]
Snowflake
ExtTbl, Iceberg Storage Integ.
Starburst
Glue, S3 AccPt VPC Endpt, min wkrs
Databricks
ExtTbl, Unity Catalog
S3 VPC Gateway Endpoint → Producer S3 Buckets (west2)
Immuta [STANDBY] — Policies synced via CI/CD
Consumer Notifications [STANDBY]
SNS→SQS: west2 SQS pre-created
Kafka: via west2 DX (pre-provisioned)
Polling API: ECS + DDB (standby)
Consumers [READY] — SQS west2 pre-created • Same CNAME endpoints
S3 CRR
▶▶
DynamoDB Global Tbl
▶▶
Glue Dual-Write
▶▶
SNS Dual-Pub
▶▶
Immuta Policy CI/CD
▶▶
Route53 Failover
▶▶
Cross-Region Synchronization (Always Active During Normal Operations)
S3 CRR east1→west2 (15-min SLA via RTC) • DynamoDB Global Tables (~2s lag) • Glue Catalog Dual-Write • SNS Dual-Publish • Route53 Failover • ECR Replication • Immuta Policy-as-Code CI/CD • Snowflake Account Replication
✔ During DR Flip: Producers reverse CRR (west2→east1), write to west2. Platform activates west2 infra. Consumers switch to west2 endpoints. Iceberg path problem eliminated (native west2 paths). RPO ≤ 15 min • RTO 45-60 min.

## Slide 3
Hybrid State — Proposed Architecture
Most producers can flip; non-flipping producers use Snowflake Private Listing (SnowGrid)
4 / 7
Data Mesh Multi-Region Resiliency — April 2026
● CAN FLIP = Ready for DR ● CANNOT FLIP = Stays in east1 ■ Snowflake Private Listing Identical to Ideal + Private Listing bridge for non-flipped producers
us-east-1 (N. Virginia)
PRIMARY / PRODUCTION
us-west-2 (Oregon)
SECONDARY / DR
FLIPPED PRODUCERS (can flip to DR)
Prod A [FLIP]
S3 east1 PRIMARY
Prod B [FLIP]
S3 east1 PRIMARY
NON-FLIPPED PRODUCERS (cannot flip)
Prod X [NO FLIP]
S3 east1 ONLY — No CRR
Prod Y [NO FLIP]
S3 east1 ONLY — No CRR
▼
Platform [ACTIVE]
Registration API • Producer Notif API • Consumer Notif API
DynamoDB (PRIMARY WRT) • SNS • Glue • Polling API • Lambdas
COMPUTE PLATFORMS [ACTIVE]
Snowflake
ALL data (flipped + non-flipped)
Starburst
ALL data
Databricks
ALL data
Snowflake east1 — PROVIDER
Unmanaged Iceberg Tables for non-flipped Prod X, Prod Y
Private Listing shares this data cross-region to west2 SF ▶
Immuta [ACTIVE]
Consumer Notifications [ACTIVE]
Consumers [ACTIVE]
FLIPPED PRODUCER S3 REPLICAS
Prod A [FLIP]
S3 west2 REPLICA
Prod B [FLIP]
S3 west2 REPLICA
NON-FLIPPED — NO S3 replica in west2 Prod X, Prod Y data only via Snowflake Private Listing
▼
Platform [WARM STANDBY]
Registration API • Producer Notif API • Consumer Notif API
DynamoDB (REPLICA RO) • SNS • Glue • Polling API • Lambdas
COMPUTE PLATFORMS [WARM STANDBY]
Snowflake
✓ Flipped data ✓ Non-flip via PL
Starburst
✓ Flipped data ✗ No non-flip
Databricks
✓ Flipped data ✗ No non-flip
◀ Snowflake west2 — CONSUMER
Receives non-flipped producer data via Private Listing
Available as shared database in west2 SF account
Immuta [STANDBY]
Consumer Notifications [STANDBY]
Consumers [READY]
S3 CRR (flipped only)
▶▶
DDB / Glue SNS
▶▶
Immuta Policy
▶▶
Private Listing
▶▶
Route53 Failover
▶▶
⚠ Hybrid Limitations: (1) Non-flipped data ONLY in Snowflake — Starburst/Databricks cannot consume Private Listing. (2) If east1 has full outage, Private Listing replication stops. (3) Must validate Private Listing + unmanaged Iceberg with Snowflake support (BCR-1528). (4) Validate Immuta governance on Private Listing shared tables.

## Slide 4
High-Level Task Breakdown
Key workstreams for Platform, Producer, and Consumer teams to enable multi-region resiliency
7 / 7
Platform Tasks
Data Mesh Platform Team
Producer Tasks
Data Producer Teams
Consumer Tasks
Data Consumer Teams
1
Setup Starburst on US-WEST-2
Provision and configure Starburst cluster in the secondary region
2
Setup Registration API & Infra on US-WEST-2
Deploy Registration API services, ECS tasks, and supporting infrastructure
3
Setup Replication of DynamoDB & Other Data
Enable DynamoDB Global Tables and replicate metadata to US-WEST-2
4
Setup Producer Notification API on US-WEST-2
Deploy producer-facing notification services in the secondary region
5
Setup Consumer Notification (API & SNS)
Deploy consumer notification API and configure SNS topics in US-WEST-2
6
Registration Changes
US-WEST-2 producer registration and Snowflake Private Listing support
7
Dex Integration / Changes
Update Dex for multi-region setup and cross-region coordination
8
Updates to Route53
Add US-WEST-2 endpoints and configure DNS failover routing policies
1
Setup US-WEST-2 Region
Provision AWS accounts, VPCs, IAM roles, and access policies
2
Replicate S3 Data to US-WEST-2
Enable S3 Cross-Region Replication for all producer datasets
3
ETL Pipeline & Glue Catalog Setup
Configure ETL pipelines and Glue Data Catalog entries for US-WEST-2
4
CADS Request
Submit Cloud Architecture & Design Services request for multi-region review
1
Setup US-WEST-2
Provision consumer AWS resources, VPCs, and IAM policies
2
Setup Consumer Pipeline in US-WEST-2
Deploy and configure data consumption pipelines in the secondary region
3
Setup SNS-SQS Connectivity on US-WEST-2
Configure SNS subscriptions and SQS queues for notifications
4
Update Connections to Global URLs
Switch compute endpoints from region-specific to global URLs for failover

## Slide 5
DR Flip Sequence
Step-by-step failover from us-east-1 to us-west-2 during a sustained regional outage
6 / 7
Data Mesh Multi-Region Resiliency — April 2026
Failover Steps
1
Assess & Approve
Confirm sustained us-east-1 outage via AWS Health Dashboard. Check S3 CRR status. Get VP Engineering approval.
5 minutes
2
Activate Platform APIs
Route53 failover → west2 ALB. DynamoDB west2 becomes write region. Scale up ECS services. Verify Lambda functions.
5-10 minutes
3
Activate Iceberg Tables
Validate latest metadata.json in west2 S3. Run register_table in west2 Glue. Verify referenced data files exist.
10-15 minutes
4
Activate Compute Platforms
Snowflake: Run external table recreation. Starburst: Scale up west2 cluster. Databricks: Activate workspace. Immuta: Verify connectivity.
10-20 min (parallel)
5
Activate Notifications
Verify SNS west2 receiving messages. Confirm Kafka flowing via west2 DX. Verify Polling API reachable via CNAME.
5 min (parallel w/ Step 4)
6
Producers Flip
Reverse CRR (west2→east1). Switch writes to west2 S3. Non-flipped: no change (Private Listing continues).
Coordinated
7
Notify Consumers & Monitor
Status: Platform operational in west2. List available vs unavailable datasets. Continuous monitoring.
5 minutes
RPO / RTO Summary
Component | RPO | RTO
S3 Data (Parquet) | 15 min | 0 min
S3 Data (Iceberg) | 15 min | 10-15 min
DynamoDB Metadata | ~2 sec | 0 min
Glue Catalog | ~0 (dual-write) | 0 min
Platform APIs | ~2 sec | 5-10 min
Snowflake (ext/Ice) | N/A | 10-20 min
Starburst | ~0 | 5-10 min
Databricks | N/A | 10-15 min
Immuta | Last CI/CD | 5-10 min
SNS→SQS (dual-pub) | ~0 | 0 min
On-Prem Kafka | ~2 sec | 5-10 min
Polling API | ~2 sec | 5-10 min
Overall Targets
≤ 15 min RPO (data loss tolerance) | 45-60 min RTO (time to restore)
Bottleneck: Snowflake external table recreation (10-20 min)
Failover Trigger
Trigger: Confirmed sustained us-east-1 outage (>15 minutes) Authority: Platform Team Lead + VP Engineering Type: Manual (with automated detection + alerting) Failback: Manual, after us-east-1 stable for >2 hours

## Slide 6
Tasks Required — Ideal State
Work by Data Mesh Platform, Producers, and Consumers to achieve full dual-region readiness
3 / 7
Data Mesh Multi-Region Resiliency — April 2026
Data Mesh Platform Team (22 tasks)
# | Task | Pri
1 | Create VPC, subnets, S3 VPC Endpoint in west2 | CRIT
2 | Deploy ECS Registration APIs in west2 (warm standby) | CRIT
3 | Deploy Producer Notification API (Lambda) in west2 | CRIT
4 | Deploy Consumer Notification API (Lambda) in west2 | CRIT
5 | Create SNS topic in west2 + cross-account subs | CRIT
6 | Configure DynamoDB Global Tables (add west2 replica) | CRIT
7 | Deploy all Lambda functions in west2 | CRIT
8 | Set up Glue Catalog in west2 + Lake Formation perms | CRIT
8a | Modify Notification Lambda for Glue dual-write (code change) | CRIT
9 | Implement SNS dual-publish (both east1 + west2 topics) | CRIT
10 | Configure Route53 failover routing + health checks | CRIT
11 | Provision Snowflake account in west2 | CRIT
12 | Build external table / Iceberg recreation automation | CRIT
13 | Deploy Starburst cluster in west2 (warm standby) | CRIT
14 | Deploy Databricks workspace in west2 | CRIT
15 | Deploy Immuta in west2 + Policy-as-Code CI/CD | CRIT
16 | Provision Direct Connect / VPN from west2 to on-prem | HIGH
17 | Build self-service producer onboarding toolkit | HIGH
18 | Build monitoring & alerting for west2 | HIGH
19 | Deploy Notification Polling API in west2 | HIGH
20 | ECR cross-region replication | HIGH
21 | Build & test DR flip runbook | HIGH
22 | Decommission plan for east1 standby after failback | MED
Producer Teams (9 tasks)
# | Task | Pri
1 | Create mirror S3 bucket in us-west-2 | CRIT
2 | Enable S3 versioning on BOTH buckets | CRIT
3 | Enable S3 CRR: east1→west2 with RTC (15-min SLA) | CRIT
4 | Grant compute platform IAM roles access to west2 bucket | CRIT
5 | Create S3 Access Points on west2 bucket (Starburst) | CRIT
6 | Enable Replication Metrics & Monitoring | HIGH
7 | Prepare CRR reversal procedure (west2→east1) | HIGH
8 | Prepare to switch writes to west2 during DR | HIGH
9 | Validate east1 write → west2 replica accessible | HIGH
Normal Ops: Producers write to east1 S3 (primary). CRR replicates to west2. During DR Flip: Producers reverse CRR (west2→east1) and switch writes to west2.
Consumer Teams (8 tasks)
# | Task | Pri
1 | Create SQS queue in us-west-2 (own account) | CRIT
2 | Subscribe west2 SQS to west2 SNS topic | CRIT
3 | Use platform CNAME endpoints (not direct URLs) | CRIT
4 | Prepare to switch polling to west2 SQS during DR | HIGH
5 | Implement idempotent message processing | HIGH
6 | On-prem Kafka: validate west2 DX path | HIGH
7 | Test end-to-end in west2 during DR drill | HIGH
8 | Document connection failover procedure | MED
Consumer Connection Strategy: • CNAME (Recommended): Platform DNS routes transparently • Snowflake Client Redirect: Native (Business Critical ed.) • Dual-Publish: Consumers can poll both SQS queues
⚠ DX Lead Time: Direct Connect / VPN from west2 to on-prem takes 4-8 weeks. Must start in Phase 1.

## Slide 7
Tasks Required — Hybrid State
Additional tasks beyond Ideal State to support non-flipping producers via Snowflake Private Listing
5 / 7
Data Mesh Multi-Region Resiliency — April 2026
Prerequisite: All Ideal State tasks (Slide 3) must be completed first. The tasks below are additional work specific to Hybrid.
Platform Team (Additional) — H1-H12
# | Task | Pri
H1 | Maintain Snowflake east1 account as Private Listing provider | CRIT
H2 | Set up SF Private Listing / SnowGrid per non-flipped producer | CRIT
H3 | Configure east1 SF as provider (share non-flipped tables) | CRIT
H4 | Configure west2 SF as consumer (subscribe to listings) | CRIT
H5 | Validate Immuta governance on PL shared tables | HIGH
H6 | Ensure non-flipped producers use CNAME for Notif API | HIGH
H7 | Build monitoring for Private Listing replication lag | HIGH
H8 | Maintain producer registry (flipped vs non-flipped) | HIGH
H9 | Document SB/DBX limitation for non-flipped data | HIGH
H10 | Build automation: hybrid → ideal transition per producer | MED
H11 | Maintain east1 SF Storage Integrations | MED
H12 | Cost tracking for Private Listing replication | MED
Non-Flipping Producer Teams (5 tasks)
# | Task | Pri
1 | Continue writing to east1 S3 (no change) | CRIT
2 | Keep east1 SF IAM role in S3 bucket policy (removing breaks PL) | CRIT
3 | Use CNAME for Producer Notification API (not direct east1 URL) | HIGH
4 | Coordinate with Platform on Private Listing setup | HIGH
5 | Commit to timeline for eventual flip to west2 | MED
Consumer Teams (Additional)
# | Task | Pri
 | Same as Ideal State (Slide 3) — consumers operate in west2 during DR | 
+1 | Understand: non-flipped data only available via Snowflake in west2 | HIGH
+2 | Accept Private Listing replication lag for non-flipped data | MED
Ideal vs. Hybrid Comparison
Aspect | Ideal | Hybrid
Producer Adoption | All can flip | Most flip; some stay east1
Iceberg Paths | ✓ Eliminated after flip | ⚠ PL for non-flipped
Snowflake | ✓ All data native | ✓ Native + PL
Starburst / DBX | ✓ Full access | ✗ No non-flip data
Complexity | Lower | Higher (two paths)
Cost | Lower | Higher (PL fees)
east1 Dependency | ✓ None during flip | ✗ Non-flip needs east1
Path Forward | Target state | Converges to Ideal
✔ Goal: Hybrid is transitional. As each non-flipping producer migrates, they move from Private Listing to native. The end state is always the Ideal Architecture.